## Sheet1
Sr. No. | Issue Description | Issue Date | Status | Resolved Date | Resolved Description
1 | Invalid user/password error message to be provided | 2020-09-07 | Pending
2 | Tournament name "IPL2020 to be provided in Dashboard | 2020-09-07 | Pending
3 | Player photograh missing. Most probably looking in root folder | 2020-09-07 | Resolved | 2020-09-07 | Image path corrected
4 | "maxWicketPlayerName" will not be available if user does not have player in his list | 2020-09-07 | Pending
5 | Word "Fanchise" need to be corrected | 2020-09-07 | Resolved
6 | Is it possible to change date format to "DD/MM/YYYY HH:MM:SS" in Franchise score board. Can use "npm install dateformat" | 2020-09-07 | Resolved
7 | I feel sequence in Franchise Score Board will be 1) Franchise 2) Owner 3) Score 4) Rank | 2020-09-07 | Resolved |  | Not to be done. Ignore
8 | String "CREATIVE TIM" along with link to be replace by Franchise Name / User Name | 2020-09-07 | Pending
9 | Web site name in Copy right to be changed to CricDream © 2020 | 2020-09-07 | Pending
10 | User name to be displayed in Dashboard (can show in Rank box) | 2020-09-07 | Pending
11 | In login page, put our name in copyright "CricDream". Else put cricdream at top (in big font) and remove copy right | 2020-09-07 | Pending
12 | Logout to be implemented | 2020-09-07 | Pending
13 | In Auction, Table looking quite emply. Can we show count of players purchased? Arun to add the field "playerCount" in /balance command | 2020-09-07 | Pending | 2020-09-07 | Arun: Added field playerCount in response. Tested ok
14 | only group members to be allowed to purhcase player (Apurva name should not come). Can used /user/group/1 for get member list | 2020-09-07 | Pending
15 | Reconfirm from admin after clicked on "Confirm" in auction | 2020-09-07 | Pending
16 | do not allow user to purchse more than 15 players. (Arun to put the code in backend to reject purchase if max count reached) | 2020-09-07 | Pending | 2020-09-07 | Arun: Added limit check. Current defined as default in app.js. Will later make it part of database. Need to test it during auction
17 | In My Team, Player name to be displayed instead of number | 2020-09-07 | Resolved
18 | Can add "About" tab in menu bar. Will give the CricDream info and contact person details | 2020-09-07 | Pending
19 |  |  | Pending
20 |  |  | Pending
21 |  |  | Pending
22 |  |  | Pending

## 9Sep2020
Admin login test (apurva) on 9th September 2020
Sr. No. | Issue Description | Priority | Issue Date | Status | Resolved Date | Resolved Description
1 | Sold button to be disabled, if already purchased | low | 2020-09-09 | Pending
2 | Reconfirm message for sold | High | 2020-09-07 | Pending
3 | RHS to automatic hide after confirmed? | High
4 | Cancel button in RHS along with Confirm | low
5 | Stat to set to IPL2020 | high
6 | Admin to get Auction start button | low |  |  |  |  | Done
7 | Unsold to be implemented | high
8 | Logout to be implemented | low
9 | Check if (as user) My team shows purchased players | high |  |  |  |  | Done
10 | (admin) My team do not get all players sold | high
11 | Extra Menu options to be added
12 | Balance not getting updated for franchisee
13 | Auction sequnce from PENDING to RUNNING working fine

## Sheet2 (hidden)
Resolved
Pending